VGL AI GOVERNANCE PORTAL

Observability — Implementation Plan

Based on VGL-OBS-SPEC-001  (OpenTelemetry AI-Agent Observability v0.1)

| Document ID | VGL-IMPL-OBS-002 |
| --- | --- |
| Version | 5.5 |
| Status | For Review |
| Prepared by | Lokanathan |
| Date | August 2026 |
| Scope | SLC-ai-governance (api/, ui/) · SLC-infra · VGL AKS (vgl-observability namespace) · All agent codebases |
| Spec reference | VGL-OBS-SPEC-001 v0.1 |

# 1.  Purpose of This Document

This plan tells the VGL development and DevOps teams exactly what to build, configure, and deploy to deliver the observability capability described in VGL-OBS-SPEC-001. Each phase has one clear goal and a done-when test that proves the requirement works.

This plan does not cover: the internal design of the observability specification, agent business logic, or detailed Collector configuration. Those belong in separate documents.

# 2.  Starting Point

Nothing in the Grafana OSS stack is deployed yet. The ELK stack is already deployed. The OTel Collector and public OTLP endpoint need to be built from scratch. All agents need to be instrumented.

| Component | Status | Notes |
| --- | --- | --- |
| Grafana OSS (dashboards, alerts) | ⬜ To deploy | Phase 1 |
| Grafana Tempo (trace backend) | ⬜ To deploy | Phase 1 — Azure Disk PV, 30-day retention |
| Grafana Mimir (metrics backend) | ⬜ To deploy | Phase 1 — Azure Blob Storage backend, 13-month retention |
| ELK Stack — Elasticsearch + Kibana | ✓ Deployed | Deployed on a dedicated VM (SHVM-VGL-AI-Governance-DEV), not on AKS. Two new indices added in Phase 1. Replaces Loki throughout. Collector sends logs to the VM over the network. |
| OTel Collector (VGL AKS) | ⬜ To deploy | Phase 1 — receives from all agents; routes to backends |
| Public OTLP endpoint otel.vglgroup.com | ⬜ To configure | Phase 1 — wildcard cert available; AGIC ingress needed |
| LiteLLM Gateway | ✓ Deployed | Primary LLM instrumentation point |
| Portal API (api/) — OTel SDK | ⬜ To instrument | Phase 2 |
| Agents — OTel SDK | ⬜ To instrument | Phase 3 |

Loki is NOT used. All log routing goes to Elasticsearch, which runs on a dedicated VM (not AKS). The OTel Collector on AKS sends logs to the VM over the network. Any spec reference to Loki is replaced by the Elasticsearch OTLP exporter throughout.

# 3.  Architecture

The VGL AI Governance Portal observability platform collects, routes and stores telemetry from AI agents, the Portal API and the LiteLLM Gateway. It gives the operations team a single place to answer three questions for any governed AI workflow: what happened (traces), how it is performing (metrics), and what exactly occurred (logs). The platform is deployed on Azure AKS and exposes a public OTLP/HTTPS endpoint (otel.vglgroup.com) so that agents running on any cloud or on-premises can send telemetry without being coupled to Azure infrastructure. This satisfies the specification's multi-cloud observability requirement while keeping the platform itself simple to operate.

The pipeline follows a simple producer → Collector → backends model:

AI Agents / Portal API / LiteLLM Gateway ¦ OpenTelemetry (OTLP) v OTel Collector (vgl-observability namespace, VGL AKS) ¦ +--------+--------+---------+ ¦ ¦ ¦ Tempo Mimir ELK Traces Metrics Logs ¦ ¦ ¦ +--------+--------+---------+ ¦ Grafana

Agents export telemetry via OTLP to otel.vglgroup.com:443 — the Collector's public OTLP/HTTP endpoint, secured with the existing wildcard certificate via AGIC. The Collector routes: traces → Tempo (AKS PV), metrics → Mimir (Azure Blob), logs → Elasticsearch (VM). Grafana provides dashboards and alerts across all three. Note: Elasticsearch runs on a dedicated VM — not inside AKS. The OTel Collector sends logs to the VM over the network using the Elasticsearch OTLP exporter.

Current Collector topology. The initial implementation deploys a multi-replica central Collector (2 replicas) in VGL AKS, load-balanced behind the Kubernetes Service and AGIC ingress. All external agents and the Portal API export directly to otel.vglgroup.com. A two-tier topology with a Local/Agent-tier DaemonSet Collector is only introduced if a governed agent runs inside VGL AKS (see O10). Detailed Collector configuration — receivers, processors, exporters, sampling, queues, redaction rules — belongs in the Collector Configuration document, not in this plan.

# 4.  Architecture Decisions

The following decisions govern this implementation. They record where the implementation diverges from spec defaults, defers functionality, or makes a deliberate architectural choice that is not self-evident from the task list alone.

| # | Decision | Rationale | Spec ref |
| --- | --- | --- | --- |
| D1 | ELK replaces Loki for log storage | Loki is not deployed in the VGL environment. ELK (Elasticsearch + Kibana) is already deployed on a dedicated VM (not on AKS) and provides equivalent log storage, search and access control. The OTel Collector on AKS sends logs to the VM over the network via the Elasticsearch OTLP exporter. All spec references to Loki are replaced by this path throughout this implementation. | §7, §10 |
| D2 | Multi-cloud agent observability supported via public OTLP endpoint | The observability platform is deployed on Azure AKS, but agents on any cloud or on-premises (AWS, GCP, other Azure subscriptions, VMs, on-premises) send telemetry to otel.vglgroup.com — a cloud-agnostic public OTLP/HTTPS endpoint. Azure-specific infrastructure choices (Blob Storage, Azure Disk, AGIC, Key Vault) are internal to the platform and invisible to agent owners. The spec's multi-cloud requirement is satisfied. | §5, §6 |
| D3 | Single central Collector for current scope; local tier conditional | All current governed agents are external (other AKS subscriptions, AWS, VM, on-premises) and export directly to otel.vglgroup.com. A Local/Agent-tier DaemonSet Collector is therefore not required in Phase 1. It is added conditionally (O10) only if a VGL AKS-resident agent is onboarded. | §5 |
| D4 | Broker / SPIFFE correlation deferred | The Identity Broker (Stage 3) is not yet live. Basic observability uses Portal agent registry ID and Wiz agent ID for correlation. When the broker is available, decision_id and spiffe_id are added to the telemetry contract and the end-to-end trace is validated. Basic observability is not blocked by this dependency. | §8, G4 |
| D5 | Content capture is off by default; opt-in per agent | Capturing gen_ai.input.messages and gen_ai.output.messages in production carries privacy and data retention risk. Content capture is disabled by default across all deployments. It is enabled only with explicit Mohammed sign-off per agent, at a sample rate of 5-10%, with content routed to the restricted vgl-ai-logs-content index (7-day retention). | §10, §15 |
| D6 | Cost metric is derived / estimated, not actual billing | vgl.gen_ai.estimated_cost.usd is calculated by multiplying token counts by a per-model price table (ConfigMap model-pricing.yaml). This is an estimate for cost attribution and governance visibility. It is not a replacement for provider invoices and should not be used for financial reconciliation without verification against actual billing. | §12 |
| D7 | Collector configuration and Agent Instrumentation Guide are separate documents | Detailed Collector configuration (receivers, processors, exporters, sampling, pipelines, redaction rules) and per-framework agent instrumentation code belong in dedicated documents, not in this implementation plan. This keeps the plan focused on what to build and how to verify it is done, not on internal engineering configuration. | N/A |

# 5.  Known Complications / Decisions Required

Items the team must be aware of before implementation begins. Raise these during planning and resolve them at the phase or task where they are required. Do not allow them to create unnecessary scope beyond the stated implementation.

| # Complication | Action required |
| --- | --- |
| C1 — Grafana OSS stack not yet deployed. All of Grafana, Tempo and Mimir must be deployed from scratch before any other phase can start. | Phase 1 is dedicated to this. Do not start Phase 2 until the Phase 1 done-when test passes. |
| C2 — Agents run different frameworks. Instrumentation differs per framework (Anthropic SDK, OpenAI SDK, LangChain, LlamaIndex, CrewAI, Node.js, custom). | Each agent owner confirms framework. Avinash/Vignesh provide the correct instrumentation pattern per the VGL Agent Instrumentation Guide. |
| C3 — Agents can run anywhere. External agents may run on AWS EKS, GCP GKE, VMs, or on-premises. Each needs a path to otel.vglgroup.com. | Provide the approved OTLP endpoint and per-environment Collector playbook. Agent owners confirm which environment type applies (O6 in Section 6) before Phase 3 begins. |
| C4 — Mimir requires Azure Blob Storage. Mimir cannot use a plain PVC for long-term metric storage. | Vijay provisions a Storage Account and container before Mimir deployment. This must be done as part of Phase 1. |
| C5 — GenAI semantic conventions are experimental. The gen_ai.* attribute names may change between semconv releases. | Pin one semconv version at implementation time. Set OTEL_SEMCONV_STABILITY_OPT_IN=gen_ai_latest_experimental on every agent and API deployment. |
| C6 — Identity Broker / SPIFFE not yet live. Spec §8 assumes a running broker emitting decision_id and SPIFFE IDs. | Basic observability must not be blocked by this dependency. Use Portal agent registry ID and Wiz agent ID initially. When the Identity Broker is available: add decision_id and spiffe_id correlation to the existing telemetry contract and validate the end-to-end trace. See also P3-2 and the agent acceptance checklist. |
| C7 — LiteLLM instrumentation coverage. Native OTel instrumentation may not cover all providers routed through LiteLLM. | Verify LiteLLM produces the required LLM telemetry in Phase 2. If native instrumentation is insufficient, add the minimum required callbacks. See VGL Agent Instrumentation Guide. |

# 6.  Implementation Phases

Five phases in order. Complete each phase's done-when test before starting the next. Phase 1 is owned by Vijay / DevOps. Development joins in Phase 2. Agent owners join in Phase 3.

| Phase | What it delivers | Primary owner |
| --- | --- | --- |
| Phase 1 — Observability Platform | Grafana, Tempo, Mimir, ELK indices, OTel Collector and otel.vglgroup.com endpoint all live. Test event verified end-to-end. | Vijay / Krapanshu |
| Phase 2 — Portal & LLM Telemetry | Portal API and LiteLLM instrumented. One test workflow visible end-to-end in Grafana. | Dev |
| Phase 3 — Agent & MCP Telemetry | Every governed agent emitting traces, metrics and logs. Complete workflow traceable in one correlated trace. | Agent owners |
| Phase 4 — Logs, Security, Governance & Derived Telemetry | Operational logs live. PII redaction active. Content controls working. Guardrail events reaching SIEM. Cost metrics visible. | Dev + Vijay / Krapanshu |
| Phase 5 — Dashboards, Validation & Rollout | Required dashboards built. End-to-end test scenarios pass. Agents progressively onboarded. | Dev + Vijay + Agent owners |

Phase 1 — Observability Platform

Goal: Grafana, Tempo, Mimir and the OTel Collector are deployed and reachable. A synthetic test event travels end-to-end and is visible in all three backends.

| Task | What to do | Owner | Done when |
| --- | --- | --- | --- |
| P1-1 | Create vgl-observability namespace. kubectl create namespace vgl-observability. Add to SLC-infra Terraform/manifests. All observability components deploy here. | Vijay / IT Team | kubectl get ns vgl-observability returns the namespace |
| P1-2 | Provision Azure Blob Storage for Mimir. Create a Storage Account (e.g. stovglobservability) and container mimir-blocks. Assign the AKS Managed Identity Storage Blob Data Contributor. | Vijay / Krapanshu | Container exists; AKS MI has write access confirmed |
| P1-3 | Deploy Grafana Mimir via Helm into vgl-observability. Use grafana/mimir-distributed (or mimir-simple). Set object store backend to Azure Blob (P1-2). Retention: 13 months. Config in SLC-infra/helm/mimir/. | Vijay / Krapanshu | Mimir pods Running; /ready returns 200 |
| P1-4 | Deploy Grafana Tempo via Helm into vgl-observability. Use grafana/tempo-distributed (or tempo-simple). PersistentVolume: Azure Disk, min 50 GB. Retention: 30 days. Config in SLC-infra/helm/tempo/. | Vijay / Krapanshu | Tempo pods Running; /ready returns 200 |
| P1-5 | Deploy Grafana OSS via Helm into vgl-observability. Configure three data sources: Tempo (traces), Mimir/Prometheus (metrics), Elasticsearch (logs). Enable Entra ID SSO via Grafana OAuth (confirm setup with Sri — O3). | Vijay / Krapanshu | Grafana UI accessible; all three data sources show green |
| P1-6 | Add two Elasticsearch indices on the VM-hosted ELK stack. (1) vgl-ai-logs-operational — 30-day ILM, all operational logs. (2) vgl-ai-logs-content — 7-day ILM, restricted Kibana access, prompt/response content. Define index templates. ELK runs on a dedicated VM (not AKS) — confirm VM hostname:port is reachable from the vgl-observability namespace with Krapanshu (O2). | Vijay / Krapanshu | Both indices exist with ILM policies applied |
| P1-7 | Deploy OTel Collector into vgl-observability. Deploy as a Deployment (2 replicas for HA), exposed through the Kubernetes Service and AGIC so OTLP traffic is load-balanced across both replicas. Receives OTLP telemetry from all agents and the Portal API via otel.vglgroup.com. Routes: traces → Tempo (AKS), metrics → Mimir (AKS), logs → Elasticsearch (VM, over network via OTLP exporter). Apply required security controls (API key auth, PII redaction, cardinality limits on metrics). Full Collector configuration in SLC-infra/helm/otel-gateway/. Note: a node-local DaemonSet Collector may be added later if VGL AKS-resident agents are onboarded (O10). | Vijay / Krapanshu | Collector pods Running (2 replicas); internal OTLP port reachable from vgl-observability namespace |
| P1-8 | Expose otel.vglgroup.com via AGIC ingress. Route otel.vglgroup.com to the Collector Service on port 4318 (OTLP/HTTP). Apply existing wildcard TLS secret. Require API key in Authorization header; store key in Key Vault kv-vgl-ai-governance-prod. | Vijay / IT Team | curl from external machine: no API key → 401; with key → 200 or 204 |
| P1-9 | Send a synthetic test event and verify end-to-end. Send an OTLP trace, metric and log to https://otel.vglgroup.com with the API key. Verify each appears in Grafana/Tempo, Grafana/Mimir and Kibana/Elasticsearch. This is the acceptance test for the entire Phase 1 platform. | Vijay | Synthetic trace, metric and log visible in Grafana/Tempo, Grafana/Mimir and Kibana/Elasticsearch |

P1 is a prerequisite for all subsequent phases. Do not start Phase 2 until P1-9 passes.

Phase 2 — Portal & LLM Telemetry

Goal: One test workflow can be followed from Portal API → LLM call → result visible in Grafana with trace ID, agent ID, token counts and errors.

| Task | What to do | Owner | Done when |
| --- | --- | --- | --- |
| P2-1 | Add OTel SDK to the Portal API (api/). Install @opentelemetry/sdk-node and @opentelemetry/auto-instrumentations-node. Create api/src/tracing.ts (see VGL Agent Instrumentation Guide). Import it as the very first line in api/src/index.ts. Set env vars in the AKS Deployment manifest: OTEL_EXPORTER_OTLP_ENDPOINT=https://otel.vglgroup.com, the required OTLP authentication header (injected from Key Vault so the SDK sends it on every request), and OTEL_SEMCONV_STABILITY_OPT_IN=gen_ai_latest_experimental. | Avinash / Vignesh | Portal API requests appear as spans in Grafana/Tempo; env vars set in Deployment manifest |
| P2-2 | Set standard resource attributes on the Portal API. In tracing.ts: service.name = vgl-ai-governance-api, service.namespace = vgl-governance, deployment.environment = dev or prod, vgl.agent.owner = team:governance. These labels appear on every trace and metric from this service. | Avinash / Vignesh | All spans in Tempo show correct service.name and vgl.agent.owner |
| P2-3 | Instrument LiteLLM calls. Verify LiteLLM produces the required LLM telemetry (gen_ai.operation.name, gen_ai.system, gen_ai.request.model, gen_ai.usage.input_tokens/output_tokens, gen_ai.response.finish_reasons, vgl.agent.id, vgl.agent.wiz_id). If native instrumentation is insufficient, add the minimum required callbacks (see VGL Agent Instrumentation Guide). Verify for Anthropic and OpenAI providers. | Avinash / Vignesh | LLM call spans visible in Tempo with token attributes; gen_ai.client.token.usage metric visible in Mimir |
| P2-4 | Add execute_tool spans for MCP calls. Wherever the Portal API calls an MCP server, wrap the call in an OTel span named execute_tool {tool_name} with: gen_ai.tool.name, gen_ai.tool.call.id, gen_ai.tool.type = mcp, mcp.method.name. Pass the W3C traceparent header outbound. | Avinash / Vignesh | MCP tool calls appear as child spans under LLM spans in Tempo waterfall |
| P2-5 | Verify required metrics are generated. Confirm gen_ai.client.operation.duration, gen_ai.client.token.usage, vgl.gen_ai.tool.duration and vgl.gen_ai.tool.errors are all visible in Grafana/Mimir after a test workflow run. | Avinash / Vijay | All four metrics visible in Mimir with correct labels |
| P2-6 | Run the end-to-end Phase 2 test. Execute one test workflow through the Portal. Confirm: one correlated trace visible in Tempo (Portal API → LLM call → MCP tool call); token and tool metrics in Mimir; operational log in Elasticsearch; all visible in Grafana. | Avinash / Vignesh | One test workflow can be followed from Portal → LLM call → result in Grafana with trace ID, agent ID, token counts and errors |

Phase 3 — Agent & MCP Telemetry

Goal: A complete governed workflow is traceable from workflow start → agent execution → LLM call → MCP tool call → result, all in one correlated trace.

This phase is for agent owners. Each agent follows the four-step instrumentation pattern in the VGL Agent Instrumentation Guide. Loka or Ajay signs off the checklist for each agent.

### Per-Agent Instrumentation (repeat for every governed agent)

| Task | What to do | Owner | Done when |
| --- | --- | --- | --- |
| P3-1 | Install OTel SDK for the agent's language and the correct GenAI auto-instrumentation package for the agent's framework. See VGL Agent Instrumentation Guide for per-framework install commands. | Agent owner | OTel SDK and framework package installed; agent code compiles |
| P3-2 | Set required env vars on the agent deployment: OTEL_EXPORTER_OTLP_ENDPOINT=https://otel.vglgroup.com (default for all current external agents; if a future VGL AKS-resident agent activates O10, use the node-local Collector endpoint instead), OTEL_SEMCONV_STABILITY_OPT_IN=gen_ai_latest_experimental, OTEL_SERVICE_NAME (unique per agent), OTEL_RESOURCE_ATTRIBUTES (service.namespace, deployment.environment, vgl.agent.owner). Also set VGL_AGENT_ID, VGL_AGENT_WIZ_ID, VGL_AGENT_SPIFFE_ID (when Identity Broker is live). Additionally, decision_id is populated per-request when broker authorisation is available. | Agent owner | All env vars present in agent deployment config |
| P3-3 | Initialise the OTel SDK in the agent's entry point before any other imports. Follow the language-specific pattern in the VGL Agent Instrumentation Guide. For Python: agent_tracing.py as the first import. For Node.js: tracing.ts as the first import. Set vgl.workflow.run_id on every span for this agent’s execution, propagated from the triggering workflow request, so that all spans from a single workflow run are identifiable in one query. | Agent owner | Agent spans appear in Grafana/Tempo with correct service.name and vgl.agent.owner |
| P3-4 | Confirm the approved telemetry export path for this agent's environment. External agents (other AKS subscriptions, AWS, VM, on-premises) export directly to https://otel.vglgroup.com using the API key from Key Vault. If the agent runs inside VGL AKS: use the node-local Collector DaemonSet if deployed (O10); otherwise export directly to otel.vglgroup.com. Vijay confirms the applicable pattern. See Known Complication C3 and O6. | Agent owner + Vijay | Test span from this environment reaches VGL Tempo |
| P3-5 | Add W3C Trace Context propagation to all MCP calls. The traceparent header must pass from the agent outbound to each MCP server call. Verify in Tempo: expected view is agent span → LLM span → execute_tool span as one connected trace. | Agent owner | Tempo shows full connected waterfall for this agent's workflow |

### Agent Acceptance Checklist — one per agent

Each agent owner completes this checklist. Loka or Ajay signs off before the agent is considered instrumented.

| # | Check | Done |
| --- | --- | --- |
| 1 | OTel SDK and framework auto-instrumentation package installed (P3-1) | ☐ |
| 2 | All required env vars set in deployment config (P3-2) | ☐ |
| 3 | SDK initialised in entry point before other imports (P3-3) | ☐ |
| 4 | Collector path confirmed for this environment (P3-4) | ☐ |
| 5 | Agent spans visible in Grafana/Tempo with correct service.name and vgl.agent.owner | ☐ |
| 6 | vgl.workflow.run_id is present on all agent spans and matches the triggering workflow request (P3-3) | ☐ |
| 7 | LLM call spans visible in Tempo with gen_ai.usage.input_tokens and gen_ai.usage.output_tokens populated | ☐ |
| 8 | W3C Trace Context propagating to MCP calls — full waterfall visible in Tempo (P3-5) | ☐ |
| 9 | Test workflow produces one correlated trace: workflow → agent → LLM → MCP tool | ☐ |
| * | If Identity Broker is available: decision_id and spiffe_id are present on spans and correlated with the trace | ☐ |

Phase 4 — Logs, Security, Governance & Derived Telemetry

Goal: Operational information is available in Grafana/ELK without exposing unauthorised content. Guardrail events reach the SIEM. Content controls work as specified.

| Task | What to do | Owner | Done when |
| --- | --- | --- | --- |
| P4-1 | Confirm operational logs are flowing to vgl-ai-logs-operational. All Portal API and agent operational log events (requests, responses, errors, timing) must appear in Elasticsearch with the correct index and retention applied. | Avinash / Vijay | Operational logs searchable in Kibana with 30-day ILM applied; each log entry carries trace_id, vgl.workflow.run_id and vgl.agent.id for correlation |
| P4-2 | Verify PII/content redaction is active. The Collector must redact or hash PII (email addresses, names, account numbers) from gen_ai.input.messages and gen_ai.output.messages before storage. Confirm the redaction regex is applied consistently at the Collector tier. | Vijay | Controlled synthetic test containing PII is processed through the Collector and the stored telemetry contains the redacted value; no unredacted PII is present in Tempo or Elasticsearch |
| P4-3 | Implement controlled content capture. Content capture (gen_ai.input.messages, gen_ai.output.messages) is OFF by default. When explicitly approved (Mohammed sign-off per agent — O5): enable for the approved workload at a sample rate of 5–10% (never 100% in production). Content routes to vgl-ai-logs-content (7-day retention, restricted Kibana access). Enabling is a change-controlled action, itself logged. | Vijay / Dev | Default: content flag absent across all deployments. When enabled: content routes to restricted index only; sample rate confirmed |
| P4-4 | Configure SIEM forwarding for guardrail/security events. Route guardrail block events (vgl.governance.decision = deny, vgl.gen_ai.guardrail.action = block) to the existing SIEM endpoint. Confirm endpoint URL and format with Ajay (O8). Guardrail events go to SIEM only — not duplicated in Elasticsearch. | Vijay / Chandan | Test guardrail block event appears in SIEM; does not appear in vgl-ai-logs-operational |
| P4-5 | Emit guardrail block metric and eval score from Portal API. (a) In enforce.ts: emit vgl.gen_ai.guardrail.blocks counter (labels: guardrail = check_name, action = block, vgl.agent.id). (b) In Governance Operations module: emit vgl.gen_ai.evals.score histogram (labels: evaluator, vgl.agent.id, tagged with trace_id). | Avinash / Vignesh | guardrail.blocks increments in Mimir on a test block; evals.score appears in Mimir when an eval runs |
| P4-6 | Add cost derivation to the Collector metrics pipeline. Multiply token counts by per-model price table (ConfigMap model-pricing.yaml in SLC-infra) to produce vgl.gen_ai.estimated_cost.usd (derived/estimated cost — not actual billing) with labels: model, vgl.agent.id, vgl.agent.owner. Confirm actual pricing with Anjali (O4). Add Mimir recording rules for daily/weekly rollup by agent and owner. | Vijay / Fin Team Lead | vgl.gen_ai.estimated_cost.usd metric visible in Mimir with correct labels; recording rules deployed |

Phase 5 — Dashboards, Validation & Rollout

Goal: An agent owner can use Grafana/ELK to diagnose a failed, slow or errant workflow run without access to raw infrastructure.

| Task | What to do | Owner | Done when |
| --- | --- | --- | --- |
| P5-1 | Build required Grafana dashboards. (a) API Overview — request rate, error rate, p95 latency. (b) LLM Usage — token usage by model, call duration, error rate. (c) Agent Overview — per-agent: LLM call rate, error rate, token usage, tool call rate, policy deny rate (vgl.agent.id as filter). (d) Cost & FinOps — daily/weekly cost per agent, per model, per owner (reviewed with Anjali). Build only dashboards the specification requires; add others only with explicit approval. | Vijay | All four dashboards show live data; vgl.agent.id filter works in Agent Overview |
| P5-2 | Configure SLO alerts. Five alert rules: (a) p95 API latency > 8 s, (b) LLM chat p95 > 4 s, (c) tool call error rate > 1%, (d) per-agent cost growth > 30% day-over-day, (e) guardrail block rate spike (> 2× baseline). Route to team Slack channel. Test each by temporarily lowering the threshold. | Vijay | All five alert rules exist; test-firing confirmed for each |
| P5-3 | Run end-to-end validation test scenarios. For each scenario below, confirm the expected observability data is present. Scenarios: (1) successful workflow — trace + metrics + logs visible; (2) failed workflow — error visible in trace, alert fires; (3) slow workflow — latency SLO alert fires; (4) LLM provider failure — LLM span has error, guardrail or fallback visible; (5) MCP tool failure — execute_tool span has error; (6) full trace correlation — one workflow ID links all spans across agent, LLM and MCP; (7) content controls — content capture flag off by default, on when approved; (8) telemetry outage — agent continues to run without blocking when Collector is unavailable. | Avinash / Vijay | All eight scenarios pass. An agent owner can diagnose a failed run in Grafana/ELK without infrastructure access |
| P5-4 | Progressively onboard agents. For each governed agent: complete Phase 3 instrumentation checklist → sign off → confirm in Agent Overview dashboard. Add to onboarding tracker in the VGL Agent Instrumentation Guide. | Loka / Agent owners | All governed agents appear in Grafana Agent Overview with live telemetry |

# 7.  Open Items

Items that need a decision or confirmation from specific people before or during implementation.

| # | Item | Needed from | Gates |
| --- | --- | --- | --- |
| O1 | Azure Blob Storage account name for Mimir — or confirm Vijay should create a new one | Vijay / Azure admin / IT Team | P1-2 |
| O2 | Elasticsearch internal service hostname:port reachable from vgl-observability namespace | Krapanshu | P1-6 |
| O3 | Grafana Entra ID SSO plugin — pre-configured or fresh setup with Sri | Vijay / Sri / IT Team | P1-5 |
| O4 | Actual LLM pricing (input/output per 1K tokens) for Anthropic Claude and OpenAI models in use | Fin Team / Ajay | P4-6 |
| O5 | Mohammed sign-off: which agents/namespaces may enable VGL_CONTENT_CAPTURE=true | Mohammed | P4-3 |
| O6 | For each external agent: confirm which environment type applies (VGL AKS / external cluster / VM / direct) before Phase 3 begins | Loka / agent owners | P3-4 |
| O7 | Verify LiteLLM version supports required instrumentation pattern. If not, confirm alternative approach | Avinash / Ajay | P2-3 |
| O8 | SIEM endpoint URL and required log format for guardrail block event forwarding | Vijay / Chandan | P4-4 |
| O9 | For each agent: confirm framework (from VGL Agent Instrumentation Guide table) before Phase 3 instrumentation begins | Loka / agent owners | P3-1 |
| O10 | If any governed agent runs inside VGL AKS: deploy a Local/Agent-tier OTel Collector DaemonSet in vgl-observability before that agent is onboarded in Phase 3. Not required for external agents (other AKS subscriptions, AWS, VM, on-premises) which export directly to otel.vglgroup.com. | Vijay | P3 gate (VGL AKS agents only) |

# 8.  Delivery Summary

| Phase | Outcome | Primary owner | Approver |
| --- | --- | --- | --- |
| Phase 1 | Grafana, Tempo, Mimir deployed in vgl-observability. ELK indices created. OTel Collector live. otel.vglgroup.com accepting authenticated OTLP. Test event verified end-to-end. | Vijay / Krapanshu | Ajay |
| Phase 2 | Portal API and LiteLLM instrumented. Traces in Tempo, metrics in Mimir, logs in ELK. Test workflow visible end-to-end in Grafana. | Avinash / Vignesh | Ajay |
| Phase 3 | Every governed agent emitting correlated telemetry. Agent acceptance checklist signed off per agent. Full workflow trace visible. | Agent owners | Loka / Ajay |
| Phase 4 | Operational logs live. PII redaction active. Content controls working. Guardrail events to SIEM. Cost metrics live. | Dev + Vijay / Krapanshu | Mohammed / Fin Team |
| Phase 5 | All required dashboards live. SLO alerts configured. All validation scenarios pass. Agents onboarded progressively. | Dev + Vijay /Krapanshu + Agent owners | Mohammed |

End of document — VGL-IMPL-OBS-002 v5.5