## Project Plan
S# | Project Name | TASK NAME | Date | Team | Ownership | Status | Remark
1 | SLC-AMS-Nexus (DTU) | High-level design (Application Flow) |  | Infra | Praveen Kachhawa
2 | SLC-AMS-Nexus (DTU) | Review for High-level design and Approval |  | Infra
3 | SLC-AMS-Nexus (DTU) | Creation Azure Subscription ¦ Region - East US |  | Infra | Pranav Bharti
4 | SLC-AMS-Nexus (DTU) | Estimated Cost for Project (DTU) |  | Infra | -
5 | SLC-AMS-Nexus (DTU) | Creation of Resource Group |  | Infra
6 | SLC-AMS-Nexus (DTU) | Creation Vnet & Subnet + Routing |  | Infra
7 | SLC-AMS-Nexus (DTU) | Private DNS Zone + Associate with VNET |  | Infra
8 | SLC-AMS-Nexus (DTU) | Terraform Script building |  | DevOps
9 | SLC-AMS-Nexus (DTU) | Resouces Creation (Terraform) |  | Infra
10 | SLC-AMS-Nexus (DTU) | Self-Hosted VM (Network Connectivity) from AKS, SLC-Terminal, PAM |  | Infra
11 | SLC-AMS-Nexus (DTU) | User Creation on Self-Hosted VM + Perquisites |  | Infra
12 | SLC-AMS-Nexus (DTU) | PAM Setup + Access |  | Infra
13 | SLC-AMS-Nexus (DTU) | PAM UserList |  | Infra
14 | SLC-AMS-Nexus (DTU) | Storage Account (Blob) Private access |  | Infra
15 | SLC-AMS-Nexus (DTU) | Storage Account (Blob) Connectivity with AKS Cluster, SelfHosted VM |  | Infra
16 | SLC-AMS-Nexus (DTU) | ACR (Use new Azure conatiner registery) |  | Infra
17 | SLC-AMS-Nexus (DTU) | ACR (Registry) Connectivity with AKS Cluster, SelfHosted VM |  | Infra
18 | SLC-AMS-Nexus (DTU) | AKS Cluster (Private access) |  | Infra
19 | SLC-AMS-Nexus (DTU) | AKS Connectivity with Application Gateway and SelfHost-VM |  | Infra
20 | SLC-AMS-Nexus (DTU) | Azure Keyvault (Private access) |  | Infra
21 | SLC-AMS-Nexus (DTU) | Keyvault Connectivity with AKS Cluster and SelfHost-VM, Application Gateway |  | Infra
22 | SLC-AMS-Nexus (DTU) | Rediscache Node (Private access) |  | Infra
23 | SLC-AMS-Nexus (DTU) | Rediscache Node connectivity with AKS, Selfhosted VM |  | Infra
24 | SLC-AMS-Nexus (DTU) | EventHub (Kafka) (Private access) |  | Infra
25 | SLC-AMS-Nexus (DTU) | EventHub (Kafka) connectivity with AKS, Selfhosted VM |  | Infra
26 | SLC-AMS-Nexus (DTU) | Network Connectivity - AMS Application & Database |  | Infra
27 | SLC-AMS-Nexus (DTU) | External Source Such GitHub |  | Infra
28 | SLC-AMS-Nexus (DTU) | ELK Monitoring Setup & Connectivity |  | Infra
29 | SLC-AMS-Nexus (DTU) | ELK Monitoring - Storage Account |  | Infra
30 | SLC-AMS-Nexus (DTU) | ELK Monitoring - Implement Shopify Accordigly (Alerting) |  | Infra
31 | SLC-AMS-Nexus (DTU) | ELK Monitoring Account Creation |  | Infra
32 | SLC-AMS-Nexus (DTU) | ELK Alerting |  | Infra
33 | SLC-AMS-Nexus (DTU) | Monitoring Site24x7 |  | Infra
34 | SLC-AMS-Nexus (DTU) | Create Github DevOps Project - Shopify-Prod |  | Infra
35 | SLC-AMS-Nexus (DTU) | Grant Access on GitHub DevOps to DevOps Team |  | Infra
36 | SLC-AMS-Nexus (DTU) | Azure Intra VGL Tenant - App Registration for SSO |  | Infra
37 | SLC-AMS-Nexus (DTU) | Access Creation for DevOps Team |  | Infra
38 | SLC-AMS-Nexus (DTU) | Access Creation for Application Team |  | Infra
39 | SLC-AMS-Nexus (DTU) | Private DNS Record Creation |  | Infra
40 | SLC-AMS-Nexus (DTU) | Public IP Address Create & Mapping with Private IP (Application Gateway & APIM) |  | Infra
41 | SLC-AMS-Nexus (DTU) | Public DNS Record Creation |  | Infra
42 | SLC-AMS-Nexus (DTU) | WAF Implementation (Prevension Mode) |  | Infra
43 | SLC-AMS-Nexus (DTU) | Low Level design Review |  | Infra
44 | SLC-AMS-Nexus (DTU) | Azure Keyvault Integration |  | DevOps
45 | SLC-AMS-Nexus (DTU) | Stoage Account Blob Integration |  | DevOps
46 | SLC-AMS-Nexus (DTU) | Database Setup |  | DBA
47 | SLC-AMS-Nexus (DTU) | Repository Creation on GitHub |  | Infra
48 | SLC-AMS-Nexus (DTU) | Grand access on GitHub Repository |  | Infra
49 | SLC-AMS-Nexus (DTU) | CI/CD Application Intregration |  | DevOps
50 | SLC-AMS-Nexus (DTU) | Application Deployment |  | DevOps
51 | SLC-AMS-Nexus (DTU) | Testing & Sanity |  | Application
52 | SLC-AMS-Nexus (DTU) | Setup Self-Hosted VM & AKS Backup |  | InfoSec
53 | SLC-AMS-Nexus (DTU) | Integration Testing |  | Application
54 | SLC-AMS-Nexus (DTU) | Funtional Testing |  | Application
55 | SLC-AMS-Nexus (DTU) | Performance Testing |  | Application
56 | SLC-AMS-Nexus (DTU) | Load Testing |  | Application
57 | SLC-AMS-Nexus (DTU) | Complete Low level design (Arch Diagram) |  | Infra

## Network
Shoplc-Dev-UAT-QC
Subscription | Shoplc-UAT
Resource Group | RG-AMS-Nexus-DUQ
Region | east-us
Network (Vnet) | VNET-SLC-AMS-DUQ-Nexus
Subnet Pool | 192.168.120.0/21
Subnet Name | Proposed Subnet | Subnet address | Range of addresses | Useable IPs | Hosts | Env | NSG | Routing | Remarks
SLC-AMS-Nexus-DUQ-AKS-Sub01 | /22 | 192.168.120.0/22 | 192.168.120.0 - 192.168.123.255 | 192.168.120.1 - 192.168.123.254 |  |  |  | RT-SLC-AMS-Nexus-DUQ-AKS-Sub01
SLC-AMS-Nexus-DUQ-AGW-Sub02 | /26 | 192.168.124.0/26 | 192.168.124.0 - 192.168.124.63 | 192.168.124.1 - 192.168.124.62 |  |  |  | RT-SLC-AMS-Nexus-DUQ-AGW-Sub02
SLC-AMS-Nexus-DUQ-Redis-Sub03 | /26 | 192.168.124.64/26 | 192.168.124.64 - 192.168.124.127 | 192.168.124.65 - 192.168.124.126 |  |  |  | RT-SLC-AMS-Nexus-DUQ-Redis-Sub03
SLC-AMS-Nexus-DUQ-DB-Sub04 | /26 | 192.168.124.128/26 | 192.168.124.128 - 192.168.124.191 | 192.168.124.129 - 192.168.124.190 |  |  |  | RT-SLC-AMS-Nexus-DUQ-DB-Sub04
SLC-AMS-Nexus-DUQ-SHVM-Sub05 | /26 | 192.168.124.192/26 | 192.168.124.192 - 192.168.124.255 | 192.168.124.193 - 192.168.124.254 |  |  |  | RT-SLC-AMS-Nexus-DUQ-SHVM-Sub05
SLC-AMS-Nexus-DUQ-Others-Sub06 | /25 | 192.168.125.0/25 | 192.168.125.0 - 192.168.125.127 | 192.168.125.1 - 192.168.125.126 |  |  |  | RT-SLC-AMS-Nexus-DUQ-Others-Sub06
Free | /25 | 192.168.125.128/25 | 192.168.125.128 - 192.168.125.255 | 192.168.125.129 - 192.168.125.254
Free | /23 | 192.168.126.0/23 | 192.168.126.0 - 192.168.127.255 | 192.168.126.1 - 192.168.127.254
Connectivity
Checklist

## Network Routes
AMS NEXUS Lower
SUB | ShopLC-UAT
RG | RG-AMS-Nexus-Lower
VNET | VNET-SLC-AMS-DUQ-Nexus
SUBNETS | SLC-AMS-Nexus-DUQ-AKS-Sub01 SLC-AMS-Nexus-DUQ-AGW-Sub02 SLC-AMS-Nexus-DUQ-Redis-Sub03 SLC-AMS-Nexus-DUQ-DB-Sub04 SLC-AMS-Nexus-DUQ-SHVM-Sub05
Route Tables
RT 1 | RT-SLC-AMS-NEXUS-AKS-Sub01
RT 2 | RT-SLC-AMS-NEXUS-AGW-Sub02
RT 3 | RT-SLC-AMS-NEXUS-SHVM-Sub05
RT 4 | RT-SLC-AMS-Nexus-DUQ-Others-Sub06
ROUTES
Name | Address Prefix | Next Hop type | Next Hop IP Address | Router Name
Internet | 0.0.0.0/0 | Virtual appliance | 172.22.216.4 | RT-SLC-AMS-Nexus-DUQ-AKS-Sub01
Internet | 0.0.0.0/0 | Virtual appliance | 172.22.216.4 | RT-SLC-AMS-Nexus-DUQ-Redis-Sub03
Internet | 0.0.0.0/0 | Virtual appliance | 172.22.216.4 | RT-SLC-AMS-Nexus-DUQ-DB-Sub04
Internet | 0.0.0.0/0 | Virtual appliance | 172.22.216.4 | RT-SLC-AMS-Nexus-DUQ-SHVM-Sub05
Internet | 0.0.0.0/0 | Virtual appliance | 172.22.216.4 | RT-SLC-AMS-Nexus-DUQ-Others-Sub06
FW_External | 172.22.215.0/25 | Virtual appliance | 172.22.216.4 | RT-SLC-AMS-Nexus-DUQ-AGW-Sub02
FW_Internal | 172.22.216.0/25 | Virtual appliance | 172.22.216.4 | RT-SLC-AMS-Nexus-DUQ-AGW-Sub02
Required Connectivity
Source
SUB | ShopLC-UAT
RG | RG-AMS-Nexus-Lower
VNET | VNET-SLC-AMS-DUQ-Nexus
AKS Sub | SLC-AMS-Nexus-DUQ-AKS-Sub01
VM Sub | SLC-AMS-Nexus-DUQ-SHVM-Sub05
VM IP | 192.168.124.196 |  | 22
SLC-AZ-UAT-Terminal | 192.168.240.100 |  | 22
PAM Access | - |  | 22
Destination
Resource | IP |  | Port
UAT DB | 192.168.240.11 |  | 1433
QC DB | 10.30.10.11 |  | 1433
SelfHosted VM | SLC-AMS-Nexus-DUQ-SHVM-Sub05 | 192.168.124.196 | 22
amscc02uat.tjc.tv | 192.168.240.21 |  | 443
atsapiuat.tjc.tv | 192.168.240.21 |  | 443
sovosapiuat.tjc.tv | 192.168.240.21 |  | 443
slcintegrationapiuat.tjc.tv | 192.168.240.21 |  | 443
Application Gateway
Name | AGTW-SLC-AMS-Nexus-Lower
Vnet | VNET-SLC-AMS-DUQ-Nexus
Subnet | SLC-AMS-Nexus-DUQ-AGW-Sub02
pvt ip | 192.168.124.10
pub ip firewall | 52.249.239.80
DNS | slcamsnexusonedev.tjc.tv
slcamsnexusgatewaydev.tjc.tv
slcamsnexusoneuat.tjc.tv
slcamsnexusgatewayuat.tjc.tv
slcamsnexusoneqc.tjc.tv
slcamsnexusgatewayqc.tjc.tv
DNS | slcamsnexusargo-lower.tjc.tv
Vnet Peering Details
Source
SUB |  | ShopLC-UAT
RG |  | RG-AMS-Nexus-Lower
Vnet |  | VNET-SLC-AMS-DUQ-Nexus
Destination
SUB |  | shoplc-cardinal
RG |  | rg-shoplc-cardinal
Vnet |  | shoplc-cardinal-hub-vnet

## Connectivity
Required Connectivity | [7 empty] | Checklist
Source |  |  |  | Port | Destination
SLC-AZ-UAT-Terminal | 192.168.240.100 |  | 22 | 22 | Ams-Nexus-Lower-SHVM | SLC-AMS-Nexus-DUQ-SHVM-Sub05 | 192.168.124.196 | Done
PAM Access | ShopLC-UAT |  | 22 | 22 | Ams-Nexus-Lower-SHVM | SLC-AMS-Nexus-DUQ-SHVM-Sub05 | 192.168.124.196 | Shahid need to confirm
Ams-Nexus-Lower-SHVM | SLC-AMS-Nexus-DUQ-SHVM-Sub05 | 192.168.124.196 | 22 | 1433 | UAT DB | 192.168.240.11 |  | Done
|  |  |  | 1433 | QC DB | 10.30.10.11 |  | Done
|  |  |  | 443 | amscc02uat.tjc.tv | 192.168.240.21 |  | Done
|  |  |  | 443 | atsapiuat.tjc.tv | 192.168.240.21 |  | Done
|  |  |  | 443 | sovosapiuat.tjc.tv | 192.168.240.21 |  | Done
|  |  |  | 443 | slcintegrationapiuat.tjc.tv | 192.168.240.21 |  | Done
SLC-AMS-Nexus-DUQ-AKS-Sub01 | SLC-AMS-Nexus-Lower-AKS |  |  | 1433 | UAT DB | 192.168.240.11 |  | Done
VNET | VNET-SLC-AMS-DUQ-Nexus |  |  | 1433 | QC DB | 10.30.10.11 |  | Done
AKS Sub | SLC-AMS-Nexus-DUQ-AKS-Sub01 |  |  | 443 | amscc02uat.tjc.tv | 192.168.240.21 |  | Done
| 192.168.120.0/22 |  |  | 443 | atsapiuat.tjc.tv | 192.168.240.21 |  | Done
|  |  |  | 443 | sovosapiuat.tjc.tv | 192.168.240.21 |  | Done
|  |  |  | 443 | slcintegrationapiuat.tjc.tv | 192.168.240.21 |  | Done
WIZ
Application Gateway | [7 empty] | Done
Name | AGTW-SLC-AMS-Nexus-Lower
Vnet | VNET-SLC-AMS-DUQ-Nexus
Subnet | SLC-AMS-Nexus-DUQ-AGW-Sub02
pvt ip | 192.168.124.10 | 52.249.239.80
pub ip firewall | 52.249.239.80
DNS | slcamsnexusonedev.tjc.tv
slcamsnexusgatewaydev.tjc.tv
slcamsnexusoneuat.tjc.tv
slcamsnexusgatewayuat.tjc.tv
slcamsnexusoneqc.tjc.tv
slcamsnexusgatewayqc.tjc.tv
DNS | slcamsnexusargo-lower.tjc.tv

## DNS
DNS | Type | Point to Private | Point to Public | Request ID
SLCAMSUat.tjc.tv | A | 192.168.240.11
SLCOP-QCDB.tjc.tv | A | 10.30.10.11
amscc02uat.tjc.tv | A | 192.168.240.21
atsapiuat.tjc.tv | A | 192.168.240.21
sovosapiuat.tjc.tv | A | 192.168.240.21
slcintegrationapiuat.tjc.tv | A | 192.168.240.21
slcamsnexusonedev.tjc.tv | A | 192.168.124.10 | 52.249.239.80 | SD Request #284866
slcamsnexusgatewaydev.tjc.tv | A | 192.168.124.10 | 52.249.239.80 | SD Request #284866
slcamsnexusoneuat.tjc.tv | A | 192.168.124.10 | 52.249.239.80 | SD Request #284866
slcamsnexusgatewayuat.tjc.tv | A | 192.168.124.10 | 52.249.239.80 | SD Request #284866
slcamsnexusoneqc.tjc.tv | A | 192.168.124.10 | 52.249.239.80 | SD Request #284866
slcamsnexusgatewayqc.tjc.tv | A | 192.168.124.10 | 52.249.239.80 | SD Request #284866
slcamsnexusargo-lower.tjc.tv | A | 192.168.124.10 | 52.249.239.80 | SD Request #284866
Project Endpoint
DNS | Type | Point to Private | Point to Public
slcamsnexusonedev.tjc.tv | A | 192.168.124.10 | 52.249.239.80
slcamsnexusgatewaydev.tjc.tv | A | 192.168.124.10 | 52.249.239.80
slcamsnexusoneuat.tjc.tv | A | 192.168.124.10 | 52.249.239.80
slcamsnexusgatewayuat.tjc.tv | A | 192.168.124.10 | 52.249.239.80
slcamsnexusoneqc.tjc.tv | A | 192.168.124.10 | 52.249.239.80
slcamsnexusgatewayqc.tjc.tv | A | 192.168.124.10 | 52.249.239.80
slcamsnexusargo-lower.tjc.tv | A | 192.168.124.10 | 52.249.239.80

## ResourceList
S# | Component | Name | Tier | Capacity | Remark
1 | Selfhosted VM (Linux) |  | Standard B2s | Standard B2s (2 vcpus, 4 GiB memory) + Premium Disk - 64 GB
2 | Application Gateway |  | Standard v2 | Instance count 1
3 | Storage Account (Blob Storage)​ |  | Standard | Replication (LRS)
4 | Azure Container Registry |  | Premium | -
5 | AKS Cluster (Private) |  | Premium | Node Pool - 2 (1System & 1User) {Total 2 Nodes)} #Standard D2ds v4 (2 vcpus, 8 GiB memory)
6 | Key Vault​ |  | Premium | -
7 | Rediscache (Azure Managed) | On Hold | Azure Managed Redis | Balanced: vCPUs: 2, Cache 0.5 GB, SKU B0
8 | Private DNS Zone |  | Standard | shoplc.com and tjc.tv
9 | Log Analytics Workspaces | On Hold | Standard | Retention (30 days) - Daily Cap 1 GB
10 | Azure App Registration
11 | Azure Managed Identity
12 | App Registration (O365) |  | - | - | Amit Kumar Shukla
13 | ELK Monitoring | - | - | #Standard D2ds v4 (2 vcpus, 8 GiB memory) + Disk 500 GB | Need to discuss
14 | Grafana Monitoring | - |  |  | Need to discuss
15 | AKS Backup |  | - | - | -
16 | GitHub - Project |  | - | - | -
Tags
| Application | SLC-AMS-Nexus (DTU)
| Application Owner | Dilip Pathak
| Cost-Center | US
| Env | DEV
| Geo IT Head | Anil Pundir
| Subscription | Resource Group | TYPE | NAME | TIER SKU | IP
| ShopLC-UAT | RG-AMS-Nexus-Lower | Application gateway | AGTW-SLC-AMS-Nexus-Lower | Standard V2 | 192.168.124.10
| ShopLC-UAT | RG-AMS-Nexus-Lower | Public IP address | agtw_public_ip | Regional | 40.121.116.179
| ShopLC-UAT | RG-AMS-Nexus-Lower | Virtual machine | Ams-Nexus-Lower-SHVM | Standard_B2s | 192.168.124.196
| ShopLC-UAT | RG-AMS-Nexus-Lower | Network Interface | Ams-Nexus-Lower-SHVM-Nic
| ShopLC-UAT | RG-AMS-Nexus-Lower | Network security group | Ams-Nexus-Lower-SHVM-NSG
| ShopLC-UAT | RG-AMS-Nexus-Lower | Disk | Ams-Nexus-Lower-SHVM_disk1_0a92c08f2bb1478baaff655d22f0b3fe | Standard HDD LRS(30Gib)
| ShopLC-UAT | RG-AMS-Nexus-Lower | Container registry | amsnexusloweracr | Premium
| ShopLC-UAT | RG-AMS-Nexus-Lower | Private endpoint | amsnexusloweracr_private_endpoint
| ShopLC-UAT | RG-AMS-Nexus-Lower | Network Interface | amsnexusloweracr_private_endpoint.nic.94b94c33-cf5f-4fb3-9cab-c8d4400dae26
| ShopLC-UAT | RG-AMS-Nexus-Lower | Private endpoint | amsnexuslowerkeyvault_private_endpoint
| ShopLC-UAT | RG-AMS-Nexus-Lower | Network Interface | amsnexuslowerkeyvault_private_endpoint.nic.7ee042d9-922a-4a1c-a26b-9e99b6287b25
| ShopLC-UAT | RG-AMS-Nexus-Lower | Storage account | amsnexuslowerstorage | StorageV2
| ShopLC-UAT | RG-AMS-Nexus-Lower | Private endpoint | amsnexuslowerstrg_private_endpoint
| ShopLC-UAT | RG-AMS-Nexus-Lower | Network Interface | amsnexuslowerstrg_private_endpoint.nic.b0b870d2-a542-4131-98b5-2645f6f19c11
| ShopLC-UAT | RG-AMS-Nexus-Lower | Key vault | keyvault-ams-nexus-lower | Premium
| ShopLC-UAT | RG-AMS-Nexus-Lower | Private DNS zone | privatelink.azurecr.io
| ShopLC-UAT | RG-AMS-Nexus-Lower | Private DNS zone | privatelink.blob.core.windows.net
| ShopLC-UAT | RG-AMS-Nexus-Lower | Private DNS zone | privatelink.vaultcore.azure.net
| ShopLC-UAT | RG-AMS-Nexus-Lower | Private DNS zone | shoplc.com
| ShopLC-UAT | RG-AMS-Nexus-Lower | Kubernetes service | SLC-AMS-Nexus-Lower-AKS | free (node size = Standard_D2ds_v4)
| ShopLC-UAT | RG-AMS-Nexus-Lower | Private DNS zone | tjc.tv
| ShopLC-UAT | RG-AMS-Nexus-Lower | Managed Identity | UAI-AMS-Nexus-Lower
| ShopLC-UAT | RG-AMS-Nexus-Lower | Virtual network | VNET-SLC-AMS-DUQ-Nexus | 192.168.120.0/21
AGTW-SLC-AMS-Nexus-Lower-PIP

## GitHub Repo
S# | GitHub Repository
1 | AMSNexus-CaseTracker
2 | AMSNexus-Customer
3 | AMSNexus-DBScripts
4 | AMSNexus-Documents
5 | AMSNexus-General
6 | AMSNexus-NexusAgents
7 | AMSNexus-NexusApiGateway
8 | AMSNexus-Nexus One
9 | AMSNexus-NexusQA
10 | AMSNexus-Order
11 | AMSNexus-PaymentIntegration
12 | AMSNexus-Product
13 | AMSNexus-RMA
14 | AMSNexus-System
15 | AMSNexus-TaxIntegration
16 | AMSNexus-WMSIntegration